## TR Status (hidden)
2021-06-08
TR No. |  | 구분 | DWG No. | Description | Rev | 동서발전 IFA 검토의견 접수 현황 |  |  | 지연여부 | Remark
Transmittal | Date |  |  |  |  | Transmittal | Date (Forecast) | 검토의견
THD-DFC-015 | 2018-05-18 | 사업 | DFC-PM-PR-0003-H | Progress Mesurement Procedure | A | EED-DFC-015 | 2018-05-21 | R
THD-DFC-016 | 2018-05-18 | 공정 | DFC-PR-PI-0010-H ~ 5001-H | P&ID | C | EED-DFC-029 | 2018-06-07 | R
TH(H)D-DFC-017 | 2018-05-25 | 사업 | DFC-PM-PR-0001-H | Project Coordination Procedure | B | EED-DFC-018 | 2018-05-30 | R
TH(H)D-DFC-018 | 2018-05-25 | 사업 | DFC-PM-PR-0003-H | Progress Mesurement Procedure | B | EED-DFC-023 | 2018-06-04 | R
TH(H)D-DFC-019 | 2018-05-25 | 공정 | DFC-PR-CA-0004-H | H2 LINE HYDRAULIC CALCULATION | A | EED-DFC-024 | 2018-06-05 | AN
TH(H)D-DFC-020 | 2018-05-25 | 공정 | DFC-PR-CA-0001-H | PSV LOAD CALCULATION | A | EED-DFC-025 | 2018-06-05 | AN
| 2018-05-25 | 공정 | DFC-PR-LI-0003-H | PSV LOAD SUMMARY | A | EED-DFC-025 | 2018-06-05 | AN
TH(H)D-DFC-021 | 2018-05-28 | 공정 | DFC-PR-DS-0003-H | Equipment Data Sheet For N2 Bottle Rack Package | C | EED-DFC-026 | 2018-06-05 | AN
TH(H)D-DFC-022 | 2018-05-28 | 공정 | DFC-PR-SP-0001-H | Basic Engineering Design Data | B | EED-DFC-020 | 2018-06-01 | R
TH(H)D-DFC-023 | 2018-05-28 | 공정 | DFC-PR-CA-0003-H | Calculation Sheet For Pump Hydraulic Calculation | A | EED-DFC-036 | 2018-06-14 | AN
| 2018-05-28 | 공정 | DFC-PR-DS-0006-H | EQUIPMENT PROCESS DATA SHEET FOR CELL DRAIN WATER PUMP | A | EED-DFC-027 | 2018-06-05 | AN
| 2018-05-28 | 공정 | DFC-PR-DS-0006-H | Equipment Data Sheet For Cell Drain Water Pump | C | EED-DFC-027 | 2018-06-05 | AN
TH(H)D-DFC-024 | 2018-06-01 | 공정 | DFC-PR-SP-0002-H | Process Description | A | EED-DFC-028 | 2018-06-05 | R
TH(H)D-DFC-025 | 2018-06-03 | 전기 | RFQ-DFC-E-001 | RFQ For 154kV GIS & Main Transformer | A | EED-DFC-019 | 2018-06-01 | R
| 2018-06-03 | 전기 | RFQ-DFC-E-002 | RFQ For 154kV Power Cable | A | EED-DFC-019 | 2018-06-01 | R
| 2018-06-03 | 전기 | RFQ-DFC-E-003 | RFQ For 154kV No.2 154kV GIS Extension | A | EED-DFC-019 | 2018-06-01 | R
TH(H)D-DFC-026 | 2018-06-03 | 공정 | DFC-PR-LI-0005-H | BATTERY LIMIT SUMMARY (TIE-IN LIST) | B | EED-DFC-030 | 2018-06-07 | AN
TH(H)D-DFC-027 | 2018-06-04 | 사업 | DFC-PM-PR-0001-H | Project Coordination Procedure | C | EED-DFC-022 | 2018-06-04 | A
TH(H)D-DFC-028 | 2018-06-04 | 전기 | DFC-EL-SD-0004-H | SINGLE LINE DIAGRAM - 한화토탈 NO.2 154KV SUBSTATION | A | EED-DFC-032 | 2018-06-08 | R
| 2018-06-04 | 전기 | DFC-EL-SD-0006-H | SINGLE LINE DIAGRAM - 154KV GIS & MAIN TRANSFORMER | A | EED-DFC-032 | 2018-06-08 | R
| 2018-06-04 | 전기 | DFC-EL-EQ-0003-H | ELECTRICAL EQUIPMENT LAYOUT - ELECTRICAL BUILDING | A | EED-DFC-032 | 2018-06-08 | R
| 2018-06-04 | 전기 | DFC-EL-PW-0005-H | MAIN CABLE ROUTE PLAN - KEY PLAN FOR 154KV UNDERGR. TRANSMISSION LINE | A | EED-DFC-032 | 2018-06-08 | R
| 2018-06-04 | 전기 | DFC-EL-SP-0002-H | TECHNICAL SPECIFICATION FOR 154KV GIS | A | EED-DFC-032 | 2018-06-08 | R
| 2018-06-04 | 전기 | DFC-EL-SP-0003-H | TECHNICAL SPECIFICATION FOR 154KV MAIN TRANSFORMER | A | EED-DFC-032 | 2018-06-08 | R
| 2018-06-04 | 전기 | RFQ-DFC-E-010 | TECHNICAL SPECIFICATION FOR NO.2 154KV GIS EXTENSION | A | EED-DFC-032 | 2018-06-08 | R
| 2018-06-04 | 전기 | DFC-EL-SP-0005-H | TECHNICAL SPECIFICATION FOR 154KV POWER CABLE | A | EED-DFC-032 | 2018-06-08 | R
| 2018-06-04 | 전기 | DFC-EL-SP-0022-H | CONSTRUCTION SPECIFICATION FOR 154KV 지중공사 및 154KV CABLE 포설공사 | A | EED-DFC-032 | 2018-06-08 | R
TH(H)D-DFC-029 | 2018-06-05 | 사업 | DFC-PM-PR-0003-H | Progress Mesurement Procedure | C | EED-DFC-031 | 2018-06-08 | A
TH(H)D-DFC-030 | 2018-06-08 | 전기 | DFC-EL-1-0100~0103, 0105, 0107~0121 | SINGLE LINE DIAGRAM | A | EED-DFC-035 | 2018-06-14 | R
TH(H)D-DFC-031 | 2018-06-08 | 전기 | DFC-EL-SP-0007-H | Technical Specification for MV Switchgear | A | EED-DFC-040 | 2018-06-18 | R
| 2018-06-08 | 전기 | DFC-EL-SP-0023-H | Technical Specification for MV Transformer | A | EED-DFC-040 | 2018-06-18 | R
TH(H)D-DFC-032 | 2018-06-08 | 공정 | DFC-PR-DS-0001-H | Equipment Data Sheet for Hydrogen Feed Gas Filter (FL-1001A/B) | C | EED-DFC-038 | 2018-06-18 | A
| 2018-06-08 | 공정 | DFC-PR-DS-0002-H | Equipment Data Sheet for Hydrogen Filter for #1~#5 Batch (FL-2101A/B~2501A/B) | C | EED-DFC-038 | 2018-06-18 | A
TH(H)D-DFC-033 | 2018-06-11 | 기계 | DFC-ME-SP-1001-H | Specification for Centrifugal Pump | A | EED-DFC-042 | 2018-06-18 | R
TH(H)D-DFC-034 | 2018-06-11 | 공정 | DFC-PR-DS-1001-H | Instrument Process Data | B | EED-DFC-037 EED-DFC-059 | 2018-06-14 2018-06-25 | R AN
TH(H)D-DFC-035 | 2018-06-12 | 전기 | DFC-EL-SP-0011-H | Technical Specification for Power Capacitor | A | EED-DFC-044 | 2018-06-19 | AN
| 2018-06-12 | 전기 | DFC-EL-SP-0012-H | Technical Specification for Induction Motor | A | EED-DFC-044 | 2018-06-19 | AN
TH(H)D-DFC-036 | 2018-06-12 | 계장 | DFC-IN-CF-0001-H | System Configuration | A | EED-DFC-039 | 2018-06-18 | R
TH(H)D-DFC-037 | 2018-06-12 | 계장 | DFC-IN-SP-0001-H | Specification for General Instrumentation | A | EED-DFC-041 | 2018-06-18 | A
| 2018-06-12 | 계장 | DFC-IN-SP-1001-H | Specification for Package Instrument | A | EED-DFC-041 | 2018-06-18 | R
| 2018-06-12 | 계장 | DFC-IN-SP-2001-H | Design Criteria for Instrumentation | A | EED-DFC-041 | 2018-06-18 | R
TH(H)D-DFC-038 | 2018-06-14 | 장치 | DFC-ME-SP-2001-H | Specification for Static Equipment | A | EED-DFC-043 | 2018-06-19 | R
TH(H)D-DFC-039 | 2018-06-15 | 전기 | DFC-EL-SD-0004-H | SINGLE LINE DIAGRAM - 한화토탈 NO.2 154KV SUBSTATION | B | EED-DFC-049 | 2018-06-19 | AN
| 2018-06-15 | 전기 | DFC-EL-SD-0006-H | SINGLE LINE DIAGRAM - 154KV GIS & MAIN TRANSFORMER | B | EED-DFC-049 | 2018-06-19 | AN
| 2018-06-15 | 전기 | DFC-EL-EQ-0003-H | ELECTRICAL EQUIPMENT LAYOUT - ELECTRICAL BUILDING | B | EED-DFC-049 | 2018-06-19 | AN
| 2018-06-15 | 전기 | DFC-EL-PW-0001-H | MAIN CABLE ROUTE PLAN - KEY PLAN FOR 154KV UNDERGR. TRANSMISSION LINE | 0 | EED-DFC-049 | 2018-06-19 | 0
| 2018-06-15 | 전기 | DFC-EL-SP-0002-H | TECHNICAL SPECIFICATION FOR 154KV GIS | 0 | EED-DFC-049 | 2018-06-19 | 0
| 2018-06-15 | 전기 | DFC-EL-SP-0003-H | TECHNICAL SPECIFICATION FOR 154KV MAIN TRANSFORMER | 0 | EED-DFC-049 | 2018-06-19 | 0
| 2018-06-15 | 전기 | DFC-EL-SP-0004-H | TECHNICAL SPECIFICATION FOR NO.2 154KV GIS EXTENSION | 0 | EED-DFC-049 | 2018-06-19 | 0
| 2018-06-15 | 전기 | DFC-EL-SP-0005-H | TECHNICAL SPECIFICATION FOR 154KV POWER CABLE | 0 | EED-DFC-049 | 2018-06-19 | 0
TH(H)D-DFC-040 | 2018-06-15 | 전기 | DFC-EL-EQ-0002-H | ELECTRICAL EQUIPMENT LAYOUT - 한화토탈 NO.2 154KV SUBSTATION GIS AREA | A | EED-DFC-048 | 2018-06-21 | A
TH(H)D-DFC-041 | 2018-06-15 | 전기 | DFC-EL-SP-0001-H | DESIGN CRITERIA FOR ELECTRICAL | A | EED-DFC-051 EED-DFC-066 | 2018-06-21 2018-06-28 | AN AN
TH(H)D-DFC-042 | 2018-06-15 | 배관 | DFC-PI-SP-0002-H | Piping Material Specification | B | EED-DFC-053 | 2018-06-21 | A
TH(H)D-DFC-043 | 2018-06-15 | 전기 | DFC-EL-LI-0001-H | Electrical Load List | A | EED-DFC-052 | 2018-06-21 | AN
TH(H)D-DFC-044 | 2018-06-18 | 공정 | DFC-PR-FD-0001-H | Process Flow Diagram - Drawing Index | C | EED-DFC-054 EED-DFC-061 | 2018-06-22 2018-06-26 | R AN
| 2018-06-18 | 공정 | DFC-PR-FD-0001-H | Process Flow Diagram - Fuel Cell Power Plant | C | EED-DFC-054 EED-DFC-061 | 2018-06-22 2018-06-26 | R AN
TH(H)D-DFC-045 | 2018-06-18 | 전기 | RFQ-DFC-E-001 | RFQ FOR 154KV GIS & MAIN TRANSFORMER | A | EED-DFC-050 | 2018-06-21 | AN
| 2018-06-18 | 전기 | RFQ-DFC-E-003 | 한화토탈 NO.2 154KV GIS EXTENSION | A | EED-DFC-050 | 2018-06-21 | A
TH(H)D-DFC-046 | 2018-06-19 | 사업 | DFC-PM-PR-0003-H | Project Measurement Procedure | 0 | 유선통화 | 2018-06-19 | R
TH(H)D-DFC-047 | 2018-06-19 | 사업 | DFC-PM-PR-0003-H | Project Measurement Procedure | D | EED-DFC-046 | 2018-06-21 | AN
TH(H)D-DFC-048 | 2018-06-19 | 계장 | DFC-IN-SL-0001-H | INSTRUMENT SYMBOLS & LEGEND | A | EED-DFC-045 | 2018-06-21 | AN
TH(H)D-DFC-049 | 2018-06-20 | 장치 | RFQ-DFC-S-002 | RFQ FOR N2 BOTTLE RACK | A | EED-DFC-065 | 2018-06-28 | AN
TH(H)D-DFC-050 | 2018-06-20 | 배관 | DFC-PI-PD-1001-H | DRAWING LIST FOR PLOT PLAN | A | EED-DFC-063 | 2018-06-27 | A
| 2018-06-20 | 배관 | DFC-PI-PD-1002-H | OVERALL PLOT PLAN | C | EED-DFC-063 | 2018-06-27 | A
| 2018-06-20 | 배관 | DFC-PI-PD-1003-H | GENERAL PLOT PLAN | C | EED-DFC-063 | 2018-06-27 | AN
| 2018-06-20 | 배관 | DFC-PI-PD-1004-H | KEY PLAN FOR PLOT PLAN | A | EED-DFC-063 | 2018-06-27 | AN
| 2018-06-20 | 배관 | DFC-PI-PD-1005-H | PLOT PLAN FOR FC BUILDING NO.1 | A | EED-DFC-063 | 2018-06-27 | AN
| 2018-06-20 | 배관 | DFC-PI-PD-1006-H | PLOT PLAN FOR FC BUILDING NO.2 | A | EED-DFC-063 | 2018-06-27 | AN
| 2018-06-20 | 배관 | DFC-PI-PD-1007-H | PLOT PLAN FOR FC BUILDING NO.3 | A | EED-DFC-063 | 2018-06-27 | AN
| 2018-06-20 | 배관 | DFC-PI-PD-1008-H | PLOT PLAN FOR FC BUILDING NO.4 | A | EED-DFC-063 | 2018-06-27 | AN
| 2018-06-20 | 배관 | DFC-PI-PD-1009-H | PLOT PLAN FOR FC BUILDING NO.5 | A | EED-DFC-063 | 2018-06-27 | AN
| 2018-06-20 | 배관 | DFC-PI-PD-1010-H | PLOT PLAN FOR FILTER STATION AREA | A | EED-DFC-063 | 2018-06-27 | AN
| 2018-06-20 | 배관 | DFC-PI-PD-1011-H | SECTION DRAWING FOR FC BUILDING (1 OF 2) | A | EED-DFC-063 | 2018-06-27 | AN
| 2018-06-20 | 배관 | DFC-PI-PD-1012-H | SECTION DRAWING FOR FC BUILDING (2 OF 2) | A | EED-DFC-063 | 2018-06-27 | AN
TH(H)D-DFC-051 | 2018-06-20 | 공정 | DFC-PR-1-0010~9002-H | P&ID | D | EED-DFC-060 | 2018-06-25 | AN
TH(H)D-DFC-052 | 2018-06-20 | 배관 | DFC-PI-SP-0001-H | DESIGN CRITERIA FOR PIPING | A | EED-DFC-064 | 2018-06-27 | R
| 2018-06-20 | 배관 | DFC-PI-SP-0003-H | ENGINEERING SPECIFICATION FOR PAINT | A | EED-DFC-064 | 2018-06-27 | R
| 2018-06-20 | 배관 | DFC-PI-SP-0004-H | ENGINEERING SPECIFICATION FOR INSULATION | A | EED-DFC-064 | 2018-06-27 | R
| 2018-06-20 | 배관 | DFC-PI-SP-0005-H | CONSTRUCTION SPECIFICATION FOR PIPING WORKS | A | EED-DFC-064 | 2018-06-27 | R
TH(H)D-DFC-053 | 2018-06-21 | 공정 | DFC-PR-LI-0001-H | Equipment List | D | EED-DFC-070 | 2018-06-29 | A
TH(H)D-DFC-054 | 2018-06-21 | 토건철 | DFC-CV-RE-0001-H | Report For Geotechnical Investigation | A | EED-DFC-057 | 2018-06-25 | R
TH(H)D-DFC-055 | 2018-06-21 | 토건철 | DFC-CV-FA-0105-H | Pile Location Plan (Overall) | A | EED-DFC-058 | 2018-06-25 | AN
| 2018-06-21 | 토건철 | DFC-CV-FA-0106-H | Pile Location Plan (1of3) | A | EED-DFC-058 | 2018-06-25 | R
| 2018-06-21 | 토건철 | DFC-CV-FA-0107-H | Pile Location Plan (2of3) | A | EED-DFC-058 | 2018-06-25 | R
| 2018-06-21 | 토건철 | DFC-CV-FA-0108-H | Pile Location Plan (3of3) | A | EED-DFC-058 | 2018-06-25 | R
TH(H)D-DFC-056 | 2018-06-21 | 배관 | DFC-PI-LI-0001-H | Piping Line List | A | EED-DFC-062 | 2018-06-27 | AN
TH(H)D-DFC-057 | 2018-06-21 | 전기 | DFC-EL-SP-0007-H | TECHNICAL SPECIFICATION FOR MV SWITCHGEAR | B | EED-DFC-056 | 2018-06-25 | A |  | TH(H)D-DFC-056 으로 잘못 나감
| 2018-06-21 | 전기 | DFC-EL-SP-0023-H | TECHNICAL SPECIFICATION FOR MV TRANSFORMER | B | EED-DFC-056 | 2018-06-25 | A |  | TH(H)D-DFC-056 으로 잘못 나감
TH(H)D-DFC-058 | 2018-06-22 | 공정 | DFC-PR-CA-0002-H | Vent Stack Calculation | B | EED-DFC-067 | 2018-06-28 | A |  | TH(H)D-DFC-057 으로 잘못 나감
TH(H)D-DFC-059 | 2018-06-22 | 배관 | DFC-PI-SD-0001-H | Standard Support Drawing | A | EED-DFC-069 | 2018-06-29 | A
TH(H)D-DFC-060 | 2018-06-22 | 공정 | DFC-PR-CA-0001-H | PSV Load Calculation | 0 | N/A | N/A | 0
| 2018-06-22 | 공정 | DFC-PR-CA-0003-H | Pump Hydraulic Calculation | 0 | N/A | N/A | 0
| 2018-06-22 | 공정 | DFC-PR-CA-0004-H | H2 Line Hydraulic Calculatio | 0 | N/A | N/A | 0
TH(H)D-DFC-061 | 2018-06-22 | 공정 | DFC-PR-DS-0001-H | Equipment Data Sheet For Hydrogen Feed Gas Filter | 0 | N/A | N/A | 0
| 2018-06-22 | 공정 | DFC-PR-DS-0002-H | Equipment Data Sheet For Hydrogen Filter For #1~#5 Batch | 0 | N/A | N/A | 0
| 2018-06-22 | 공정 | DFC-PR-DS-0003-H | Equipment Data Sheet For N2 Bottle Rack Package | 0 | N/A | N/A | 0
| 2018-06-22 | 공정 | DFC-PR-DS-0006-H | Equipment Data Sheet For Cell Drain Water Pump | 0 | N/A | N/A | 0
TH(H)D-DFC-062 | 2018-06-22 | 공정 | DFC-PR-LI-0003-H | PSV Load Summary | 0 | N/A | N/A | 0
| 2018-06-22 | 공정 | DFC-PR-LI-0005-H | Battery Limit for Field | 0 | N/A | N/A | 0
TH(H)D-DFC-063 | 2018-06-25 | 공정 | DFC-PR-SP-0002-H | Process Description | B | EED-DFC-075 | 2018-07-03 | AN
TH(H)D-DFC-064 | 2018-06-25 | 전기 | DFC-EL-SP-0011-H | TECHNICAL SPECIFICATION FOR POWER CAPACITOR | 0 | N/A | N/A | 0
| 2018-06-25 | 전기 | DFC-EL-SP-0012-H | TECHNICAL SPECIFICATION FOR INDUCTION MOTOR | 0 | N/A | N/A | 0
TH(H)D-DFC-065 | 2018-06-25 | 소방 | DFC-FF-SP-0001-H | Construction Specification for Fire Fighting System | A | EED-DFC-076 | 2018-07-03 | AN
| 2018-06-25 | 설비 | DFC-HV-SP-0001-H | Design Criteria for HVAC&Plumbing | A | EED-DFC-076 | 2018-07-03 | AN
| 2018-06-25 | 설비 | DFC-HV-SP-0002-H | Technical Specification for HVAC&Plumbing | A | EED-DFC-076 | 2018-07-03 | AN
| 2018-06-25 | 설비 | DFC-HV-SP-0003-H | Construction Specification for HVAC&Plumbing | A | EED-DFC-076 | 2018-07-03 | AN
TH(H)D-DFC-066 | 2018-06-27 | 기계 | DFC-ME-SP-1001-H | Specification for Centrifugal Pump | B | EED-DFC-072 | 2018-07-02 | A
TH(H)D-DFC-067 | 2018-06-27 | 전기 | RFQ-DFC-E-001 | RFQ FOR 154KV GIS & MAIN TRANSFORMER | 0 | N/A | N/A | 0
| 2018-06-27 | 전기 | RFQ-DFC-E-003 | RFQ FOR 한화토탈 NO.2 154KV GIS EXTENSION | 0 | N/A | N/A | 0
TH(H)D-DFC-068 | 2018-06-28 | 공정 | DFC-PR-SP-0001-H | Basic Engineering Design Data | C | EED-DFC-078 | 2018-07-04 | AN
TH(H)D-DFC-069 | 2018-06-28 | 배관 | DFC-PI-SP-0002-H | Piping Material Specification | 0 | N/A | N/A | 0
TH(H)D-DFC-070 | 2018-06-28 | 소방 | DFC-FF-LI-0001-H | Drawing List | A | EED-DFC-079 | 2018-07-05 | A
| 2018-06-28 | 소방 | DFC-FF-SL-0001-H | Symbol & Legend | A | EED-DFC-079 | 2018-07-05 | A
| 2018-06-28 | 소방 | DFC-FF-PI-1001-H | P&ID for Fire Water Distribution System | A | EED-DFC-079 | 2018-07-05 | AN
| 2018-06-28 | 소방 | DFC-FF-PI-1002-H | P&ID for Clean Agent System – Electrical Building | A | EED-DFC-079 | 2018-07-05 | AN
| 2018-06-28 | 소방 | DFC-FF-PI-1003-H | P&ID for Indoor Hydrant System –F/C Building No.1 | A | EED-DFC-079 | 2018-07-05 | A
| 2018-06-28 | 소방 | DFC-FF-PI-1004-H | P&ID for Indoor Hydrant System –F/C Building No.2 | A | EED-DFC-079 | 2018-07-05 | A
| 2018-06-28 | 소방 | DFC-FF-PI-1005-H | P&ID for Indoor Hydrant System –F/C Building No.3 | A | EED-DFC-079 | 2018-07-05 | A
| 2018-06-28 | 소방 | DFC-FF-PI-1006-H | P&ID for Indoor Hydrant System –F/C Building No.4 | A | EED-DFC-079 | 2018-07-05 | A
| 2018-06-28 | 소방 | DFC-FF-PI-1007-H | P&ID for Indoor Hydrant System –F/C Building No.5 | A | EED-DFC-079 | 2018-07-05 | A
TH(H)D-DFC-071 | 2018-06-29 | 전기 | DFC-EL-SP-0022-H | Construction Specification for 154kV 지중공사 및 154kV Cable 포설공사 | B
TH(H)D-DFC-072 | 2018-06-29 | 토건철 | DFC-CV-FA-0105-H | PILE LOCATION PLAN(OVERALL) | 0 | N/A | N/A | 0
| 2018-06-29 | 토건철 | DFC-CV-FA-0106-H | PILE LOCATION PLAN(1of3) | B | EED-DFC-073 | 2018-07-06 | A
| 2018-06-29 | 토건철 | DFC-CV-FA-0107-H | PILE LOCATION PLAN(2of3) | B | EED-DFC-073 | 2018-07-06 | A
| 2018-06-29 | 토건철 | DFC-CV-FA-0108-H | PILE LOCATION PLAN(3of3) | B | EED-DFC-073 | 2018-07-06 | A
TH(H)D-DFC-073 | 2018-07-03 | 전기 | DFC-EL-SP-0007-H | Technical Specification for MV Switchgear | 0 | N/A | N/A | 0
| 2018-07-03 | 전기 | DFC-EL-SP-0023-H | Technical Specification for MV Transformer | 0 | N/A | N/A | 0
TH(H)D-DFC-074 | 2018-07-04 | 계장 | DFC-IN-SL-0001-H | Instrument Symbols & Legend_Rev.0 제출 | 0 | N/A | N/A | 0
TH(H)D-DFC-075 | 2018-07-04 | 장치 | RFQ-DFC-S-001 | RFQ for Filter Rev.A 제출 | A
TH(H)D-DFC-076 | 2018-07-04 | 계장 | DFC-IN-SP-0001-H | Specification for General Instrumentation | 0 | N/A | N/A | 0
TH(H)D-DFC-077 | 2018-07-04 | 계장 | DFC-IN-SP-1001-H | Specification for Package Instrument | B
| 2018-07-04 | 계장 | DFC-IN-SP-2001-H | Design Criteria for Instrument | B
TH(H)D-DFC-078 | 2018-07-04 | 공정 | DFC-PR-FD-0001-H | Process Flow Diagram | 0 | N/A | N/A | 0
| 2018-07-04 | 공정 | DFC-PR-FD-0002-H | Process Flow Diagram | 0 | N/A | N/A | 0
TH(H)D-DFC-079 | 2018-07-04 | 토건철 | DFC-CV-SP-0001-H | DESIGN CRITERIA | A
| 2018-07-04 | 토건철 | DFC-CV-SP-0002-H | SPECIFICATION FOR CIVIL CONSTRUCTION | A
| 2018-07-04 | 토건철 | DFC-ST-SP-0003-H | SPECIFICATION FOR STEEL STRUCTURAL CONSTRUCTION | A
| 2018-07-04 | 토건철 | DFC-AR-SP-0004-H | SPECIFICATION FOR ARCHITECTURAL CONSTRUCTION | A
TH(H)D-DFC-080 | 2018-07-04 | 기계 | DFC-ME-SP-1001-H | REPORT FOR GEOTECHNICAL INVESTIGATION | 0 | N/A | N/A | 0
TH(H)D-DFC-081 | 2018-07-04 | 사업 | DFC-PM-P-003 | Progress Measurement Procedure Rev.0 제출 | 0 | N/A | N/A | 0
TH(H)D-DFC-082 | 2018-07-04 | QC | DFC-PM-PR-0004-H | General Inspection Requirement for Procurement | A
TH(H)D-DFC-083 | 2018-07-05 | 공정 장치 | DFC-PR-DS-1001-H RFQ-DFC-S-002 | INSTRUMENT PROCESS DATA RFQ FOR N2 BOTTLE RACK PACKAGE | 0 0 | N/A | N/A | 0
TH(H)D-DFC-084 | 2018-07-05 | 공정 | DFC-PR-DS-0005-H DFC-PR-DS-0004-H | CELL DRAIN WATER PIT N2 BOTTLE RACK PACKAGE FOR H2 HEADER | C C
TH(H)D-DFC-085 | 2018-07-06 | 전기 | DFC-EL-SP-0022-H | CONSTRUCTION SPECIFICATION FOR 154KV 지중공사 및 154KV CABLE 포설공사 | 0 | N/A | N/A | 0
TH(H)D-DFC-086 | 2018-07-06 | 기계 | RFQ-DFC-R-002 | RFQ FOR VERTICAL SUMP PUMP | A
TH(H)D-DFC-087 | 2018-07-06 | 토건철 |  | STANDARD DRAWING 45건 | A
TH(H)D-DFC-088 | 2018-07-06 | 공정 | DFC-PR-LI-0001-H DFC-PR-CA-0002-H | Process Equipment List Process Vent Stack Calculation | 0 0 | N/A | N/A | 0 0
TH(H)D-DFC-089 | 2018-07-06 | 전기 | RFQ-DFC-E-002 | RFQ FOR 154KV POWER CABLE | A
TH(H)D-DFC-090 | 2018-07-09 | 공정 | DFC-PR-SP-0002-H | Process Description | 0 | N/A | N/A | 0
TH(H)D-DFC-091 | 2018-07-11 | 공정 | DFC-PR-LI-0002-H | Utility Summary | A
TH(H)D-DFC-092 | 2018-07-13 | 전기 | DFC-EL-CA-0008-H | Calculation For Grounding Resistance | A
| 2018-07-13 | 전기 | DFC-EL-GR-0002-H | GROUNDING PLAN - OVERALL | A
| 2018-07-13 | 전기 | DFC-EL-GR-0003-H | GROUNDING PLAN - 1 | A
| 2018-07-13 | 전기 | DFC-EL-GR-0004-H | GROUNDING PLAN - 2 | A
| 2018-07-13 | 전기 | DFC-EL-GR-0005-H | GROUNDING PLAN - 3 | A
TH(H)D-DFC-093 | 2018-07-13 | 전기 | DFC-EL-CA-0001-H | CALCULATION FOR TRANSFORMER CAPACITY | A
TH(H)D-DFC-094 | 2018-07-13 | 전기 | DFC-EL-SP-0008-H | TECHNICAL SPECIFICATION FOR BUSDUCT | A
TH(H)D-DFC-095 | 2018-07-13 | 토건철 | DFC-CV-FA-0105-H | Pile Location Plan (Overall) | 0 | N/A | N/A | 0
| 2018-07-13 | 토건철 | DFC-CV-FA-0106-H | Pile Location Plan (1of3) | 0 | N/A | N/A | 0
| 2018-07-13 | 토건철 | DFC-CV-FA-0107-H | Pile Location Plan (2of3) | 0 | N/A | N/A | 0
| 2018-07-13 | 토건철 | DFC-CV-FA-0108-H | Pile Location Plan (3of3) | 0 | N/A | N/A | 0
TH(H)D-DFC-096 | 2018-07-13 | 전기 | RFQ-DFC-E-002 | RFQ FOR 154KV POWER CABLE | 0 | N/A | N/A | 0
TH(H)D-DFC-097 | 2018-07-13 | 전기 | DFC-EL-CA-0003-H | CALCULATION FOR UPS CAPACITY | A
| 2018-07-13 | 전기 | DFC-EL-CA-0004-H | CALCULATION FOR BATTERY CHARGER & BATTERY CAPACITY | A
| 2018-07-13 | 전기 | DFC-EL-SP-0013-H | TECHNICAL SPECIFICATION FOR AC UPS | A
| 2018-07-13 | 전기 | DFC-EL-SP-0014-H | TECHNICAL SPECIFICATION FOR DC BATTERY CHARGER | A
TH(H)D-DFC-098 | 2018-07-16 | 공정 | DFC-PR-SP-0001-H | BASIC ENGINEERING DESIGN DATA | 0
| 2018-07-16 | 장치 | DFC-ME-SP-2001-H | DESIGN CRITERIA FOR STATIC EQUIPMENT | 0
| 2018-07-16 | FF | DFC-FF-SP-0001-H | CONSTRUCTION SPECIFICATION FOR FIRE FIGHTING SYSTEM | 0
TH(H)D-DFC-099 | 2018-07-16 | 배관 | DFC-PI-SP-0001-H | DESIGN CRITERIA FOR PIPING | B
| 2018-07-16 | 배관 | DFC-PI-SP-0003-H | ENGINEERING SPECIFICATION FOR PAINT | B
| 2018-07-16 | 배관 | DFC-PI-SP-0004-H | ENGINEERING SPECIFICATION FOR INSULATION | B
| 2018-07-16 | 배관 | DFC-PI-SP-0005-H | CONSTRUCTION SPECIFICATION FOR PIPING WORKS | B
TH(H)D-DFC-100 | 2018-07-16 | 배관 | DFC-PI-SD-0001-H | STANDARD SUPPORT DRAWING | 0
TH(H)D-DFC-101 | 2018-07-16 | QC | DFC-PM-PR-0004-H | General Inspection Requirement for Procurement | B
TH(H)D-DFC-102 | 2018-07-16 | 배관 | RFQ-DFC-P-009-01 | RFQ for Forged Valve | A
| 2018-07-16 | 배관 | RFQ-DFC-P-010-01 | RFQ for Cast Val | A
| 2018-07-16 | 배관 | RFQ-DFC-P-012-01 | RFQ for Ball Valve | A
TH(H)D-DFC-103 | 2018-07-16 | 장치 | RFQ-DFC-S-001 | RFQ for Filter | 0
TH(H)D-DFC-104 | 2018-07-16 | 토건철 |  | Fuel Cell Structure Batch No.4 Rev.A 제출의 건 | A

## DCL Process
| project ID | Category(1) | Category(2)
No. | project ID | category ID | Doc. No. | Doc. Title | Start |  |  | IFA Issue (A) |  |  | IFA Approval |  |  | IFA Issue(REV.B) |  |  |  | IFA Issue(REV.C) |  |  |  | IFA Issue(REV.D) |  |  |  | AFC Issue(REV.0) |  |  | AFC ApprovalREV.0) |  |  |  | AFC Issue(REV.1) |  |  |  | AFC Issue(REV.2) |  |  |  | AFC Issue(REV.3) |  |  |  | AFC Issue(REV.4) |  |  |  | AFC Issue(REV.5) |  |  |  | As-Built
[5 empty] | P | F | A | P | F | A | P | F | A | P | A | 회신일 | 승인결과 | P | A | 회신일 | 승인결과 | P | A | 회신일 | 승인결과 | P | F | A | P | F | A | 승인결과 | P | A | 회신일 | 승인결과 | P | A | 회신일 | 승인결과 | P | A | 회신일 | 승인결과 | P | A | 회신일 | 승인결과 | P | A | 회신일 | 승인결과 | P | F | A
A | TK-2021-001 | process | 설계기준서 | /design_spec
1 |  |  | TEP-PR-SP-0001-P | Plant 운전 일반 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-03-25; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
2 |  |  | TEP-PR-SP-0002-P | 일반설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-03-23; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
3 |  |  | TEP-PR-SP-0003-P | 바이패스 계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-04-16; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
4 |  |  | TEP-PR-SP-0004-P | 주증기 계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-04-16; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
5 |  |  | TEP-PR-SP-0005-P | 복수계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-03-23; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
6 |  |  | TEP-PR-SP-0006-P | 냉각수 계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-04-16; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
7 |  |  | TEP-PR-SP-0007-P | 급수계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-03-25; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
8 |  |  | TEP-PR-SP-0008-P | 기기냉각수 계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-04-16; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
9 |  |  | TEP-PR-SP-0009-P | 수처리계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-03-25; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
10 |  |  | TEP-PR-SP-0010-P | 보조증기 계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-03-23; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
11 |  |  | TEP-PR-SP-0011-P | 압축공기 계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-04-16; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
12 |  |  | TEP-PR-SP-0012-P | Vent and Drain 계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-03-25; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
13 |  |  | TEP-PR-SP-0013-P | 약품주입계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-03-25; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
14 |  |  | TEP-PR-SP-0014-P | 시료채취계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-03-23; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
15 |  |  | TEP-PR-SP-0015-P | 서비스가스 계통 설계기준서 | Start P: 2021-02-10; Start F: 2018-05-04; Start A: 2021-02-10; IFA Issue (A) P: 2021-03-25; IFA Issue (A) F: 2018-05-18; IFA Issue (A) A: 2021-03-23; IFA Approval P: 2021-04-22; IFA Approval F: 2018-06-25; IFA Issue(REV.C) 승인결과: □ 승인 ■ 수정요망; IFA Issue(REV.D) 승인결과: □ 승인 ■ 조건부 승인; AFC Issue(REV.0) P: 2021-05-15; AFC ApprovalREV.0) P: 2021-06-15; AFC ApprovalREV.0) 승인결과: □ 승인 □ 수정요망; AFC Issue(REV.1) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.2) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.3) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.4) 승인결과: ■ 승인 □ 수정요망; AFC Issue(REV.5) 승인결과: □ 승인 □ 수정요망; As-Built P: 2024-03-31
[41 empty] | 2019-08-28 | 2019-08-28 | 2019-09-17
Note on AI6: 이정미(LEE JUNG MI): TR-302
Note on AJ6: 이정미(LEE JUNG MI): EED-271
Note on AK6: 이정미(LEE JUNG MI): 회신 No.
Note on AM6: 이정미(LEE JUNG MI): TR-465
Note on AN6: 이정미(LEE JUNG MI): EED-441
Note on AO6: 이정미(LEE JUNG MI): 회신 No.
Note on AQ6: 이정미(LEE JUNG MI): TR-564
Note on AR6: 이정미(LEE JUNG MI): EED-796
Note on AU6: 이정미(LEE JUNG MI): TR-586
Note on AV6: 이정미(LEE JUNG MI): EED-849
Note on AY6: 이정미(LEE JUNG MI): TR-595
Note on AI7: 이정미(LEE JUNG MI): TR-302
Note on AJ7: 이정미(LEE JUNG MI): EED-271
Note on AK7: 이정미(LEE JUNG MI): 회신 No.
Note on AM7: 이정미(LEE JUNG MI): TR-465
Note on AN7: 이정미(LEE JUNG MI): EED-441
Note on AO7: 이정미(LEE JUNG MI): 회신 No.
Note on AQ7: 이정미(LEE JUNG MI): TR-564
Note on AR7: 이정미(LEE JUNG MI): EED-796
Note on AU7: 이정미(LEE JUNG MI): TR-586
Note on AV7: 이정미(LEE JUNG MI): EED-849
Note on AY7: 이정미(LEE JUNG MI): TR-595
Note on AI8: 이정미(LEE JUNG MI): TR-302
Note on AJ8: 이정미(LEE JUNG MI): EED-271
Note on AK8: 이정미(LEE JUNG MI): 회신 No.
Note on AM8: 이정미(LEE JUNG MI): TR-465
Note on AN8: 이정미(LEE JUNG MI): EED-441
Note on AO8: 이정미(LEE JUNG MI): 회신 No.
Note on AQ8: 이정미(LEE JUNG MI): TR-564
Note on AR8: 이정미(LEE JUNG MI): EED-796
Note on AU8: 이정미(LEE JUNG MI): TR-586
Note on AV8: 이정미(LEE JUNG MI): EED-849
Note on AY8: 이정미(LEE JUNG MI): TR-595
Note on AI9: 이정미(LEE JUNG MI): TR-302
Note on AJ9: 이정미(LEE JUNG MI): EED-271
Note on AM9: 이정미(LEE JUNG MI): TR-465
Note on AN9: 이정미(LEE JUNG MI): EED-441
Note on AO9: 이정미(LEE JUNG MI): 회신 No.
Note on AQ9: 이정미(LEE JUNG MI): TR-564
Note on AR9: 이정미(LEE JUNG MI): EED-796
Note on AU9: 이정미(LEE JUNG MI): TR-586
Note on AV9: 이정미(LEE JUNG MI): EED-849
Note on AY9: 이정미(LEE JUNG MI): TR-595
Note on AI10: 이정미(LEE JUNG MI): TR-302
Note on AJ10: 이정미(LEE JUNG MI): EED-271
Note on AM10: 이정미(LEE JUNG MI): TR-465
Note on AN10: 이정미(LEE JUNG MI): EED-441
Note on AO10: 이정미(LEE JUNG MI): 회신 No.
Note on AQ10: 이정미(LEE JUNG MI): TR-564
Note on AR10: 이정미(LEE JUNG MI): EED-796
Note on AU10: 이정미(LEE JUNG MI): TR-586
Note on AV10: 이정미(LEE JUNG MI): EED-849
Note on AY10: 이정미(LEE JUNG MI): TR-595
Note on AI11: 이정미(LEE JUNG MI): TR-302
Note on AJ11: 이정미(LEE JUNG MI): EED-271
Note on AM11: 이정미(LEE JUNG MI): TR-465
Note on AN11: 이정미(LEE JUNG MI): EED-441
Note on AO11: 이정미(LEE JUNG MI): 회신 No.
Note on AR11: 이정미(LEE JUNG MI): EED-796
Note on AU11: 이정미(LEE JUNG MI): TR-586
Note on AV11: 이정미(LEE JUNG MI): EED-849
Note on AY11: 이정미(LEE JUNG MI): TR-595
Note on AI12: 이정미(LEE JUNG MI): TR-302
Note on AJ12: 이정미(LEE JUNG MI): EED-271
Note on AK12: 이정미(LEE JUNG MI): 회신 No.
Note on AM12: 이정미(LEE JUNG MI): TR-465
Note on AN12: 이정미(LEE JUNG MI): EED-441
Note on AO12: 이정미(LEE JUNG MI): 회신 No.
Note on AQ12: 이정미(LEE JUNG MI): TR-564
Note on AR12: 이정미(LEE JUNG MI): EED-796
Note on AU12: 이정미(LEE JUNG MI): TR-586
Note on AV12: 이정미(LEE JUNG MI): EED-849
Note on AY12: 이정미(LEE JUNG MI): TR-595
Note on AI13: 이정미(LEE JUNG MI): TR-302
Note on AJ13: 이정미(LEE JUNG MI): EED-271
Note on AK13: 이정미(LEE JUNG MI): 회신 No.
Note on AM13: 이정미(LEE JUNG MI): TR-465
Note on AN13: 이정미(LEE JUNG MI): EED-441
Note on AO13: 이정미(LEE JUNG MI): 회신 No.
Note on AQ13: 이정미(LEE JUNG MI): TR-564
Note on AR13: 이정미(LEE JUNG MI): EED-796
Note on AU13: 이정미(LEE JUNG MI): TR-586
Note on AV13: 이정미(LEE JUNG MI): EED-849
Note on AY13: 이정미(LEE JUNG MI): TR-595
Note on AI14: 이정미(LEE JUNG MI): TR-302
Note on AJ14: 이정미(LEE JUNG MI): EED-271
Note on AK14: 이정미(LEE JUNG MI): 회신 No.
Note on AM14: 이정미(LEE JUNG MI): TR-465
Note on AN14: 이정미(LEE JUNG MI): EED-441
Note on AO14: 이정미(LEE JUNG MI): 회신 No.
Note on AQ14: 이정미(LEE JUNG MI): TR-564
Note on AR14: 이정미(LEE JUNG MI): EED-796
Note on AU14: 이정미(LEE JUNG MI): TR-586
Note on AV14: 이정미(LEE JUNG MI): EED-849
Note on AY14: 이정미(LEE JUNG MI): TR-595
Note on AI15: 이정미(LEE JUNG MI): TR-302
Note on AJ15: 이정미(LEE JUNG MI): EED-271
Note on AK15: 이정미(LEE JUNG MI): 회신 No.
Note on AN15: 이정미(LEE JUNG MI): EED-441
Note on AO15: 이정미(LEE JUNG MI): 회신 No.
Note on AQ15: 이정미(LEE JUNG MI): TR-564
Note on AR15: 이정미(LEE JUNG MI): EED-796
Note on AU15: 이정미(LEE JUNG MI): TR-586
Note on AV15: 이정미(LEE JUNG MI): EED-849
Note on AY15: 이정미(LEE JUNG MI): TR-595
Note on AI16: 이정미(LEE JUNG MI): TR-302
Note on AJ16: 이정미(LEE JUNG MI): EED-271
Note on AK16: 이정미(LEE JUNG MI): 회신 No.
Note on AN16: 이정미(LEE JUNG MI): EED-441
Note on AO16: 이정미(LEE JUNG MI): 회신 No.
Note on AQ16: 이정미(LEE JUNG MI): TR-564
Note on AR16: 이정미(LEE JUNG MI): EED-796
Note on AU16: 이정미(LEE JUNG MI): TR-586
Note on AV16: 이정미(LEE JUNG MI): EED-849
Note on AY16: 이정미(LEE JUNG MI): TR-595
Note on AI17: 이정미(LEE JUNG MI): TR-302
Note on AJ17: 이정미(LEE JUNG MI): EED-271
Note on AK17: 이정미(LEE JUNG MI): 회신 No.
Note on AN17: 이정미(LEE JUNG MI): EED-441
Note on AO17: 이정미(LEE JUNG MI): 회신 No.
Note on AQ17: 이정미(LEE JUNG MI): TR-564
Note on AR17: 이정미(LEE JUNG MI): EED-796
Note on AU17: 이정미(LEE JUNG MI): TR-586
Note on AV17: 이정미(LEE JUNG MI): EED-849
Note on AY17: 이정미(LEE JUNG MI): TR-595
Note on AI18: 이정미(LEE JUNG MI): TR-302
Note on AJ18: 이정미(LEE JUNG MI): EED-271
Note on AK18: 이정미(LEE JUNG MI): 회신 No.
Note on AN18: 이정미(LEE JUNG MI): EED-441
Note on AO18: 이정미(LEE JUNG MI): 회신 No.
Note on AQ18: 이정미(LEE JUNG MI): TR-564
Note on AR18: 이정미(LEE JUNG MI): EED-796
Note on AU18: 이정미(LEE JUNG MI): TR-586
Note on AV18: 이정미(LEE JUNG MI): EED-849
Note on AY18: 이정미(LEE JUNG MI): TR-595
Note on AI19: 이정미(LEE JUNG MI): TR-302
Note on AJ19: 이정미(LEE JUNG MI): EED-271
Note on AK19: 이정미(LEE JUNG MI): 회신 No.
Note on AN19: 이정미(LEE JUNG MI): EED-441
Note on AO19: 이정미(LEE JUNG MI): 회신 No.
Note on AQ19: 이정미(LEE JUNG MI): TR-564
Note on AR19: 이정미(LEE JUNG MI): EED-796
Note on AU19: 이정미(LEE JUNG MI): TR-586
Note on AV19: 이정미(LEE JUNG MI): EED-849
Note on AY19: 이정미(LEE JUNG MI): TR-595
Note on AI20: 이정미(LEE JUNG MI): TR-302
Note on AJ20: 이정미(LEE JUNG MI): EED-271
Note on AK20: 이정미(LEE JUNG MI): 회신 No.
Note on AN20: 이정미(LEE JUNG MI): EED-441
Note on AO20: 이정미(LEE JUNG MI): 회신 No.
Note on AQ20: 이정미(LEE JUNG MI): TR-564
Note on AR20: 이정미(LEE JUNG MI): EED-796
Note on AU20: 이정미(LEE JUNG MI): TR-586
Note on AV20: 이정미(LEE JUNG MI): EED-849
Note on AY20: 이정미(LEE JUNG MI): TR-595